## Dashboard Summary
I. Requirements and Test Cases Coverage
Release Scope |  |  | Requirements | Test Cases | Unmapped Requirements | Unmapped Test Cases | Requirements Coverage | Test Cases Coverage
Total |  |  | 31 | 31 | 0 | 0 | 100% | 100%
| Within Scope of New Release |  | 25 | 25 | 0 | 0 | 100% | 100%
| Existed in Previous Release |  | 6 | 6 | 0 | 0 | 100% | 100%
Total (unique) |  |  | 30 | 30
| Requirements | Test Cases |  | Requirements | Test Cases
Old | 6 | 6 | Mapped | 31 | 31
New | 25 | 25 | Unmapped | 0 | 0
II. Test Cases Executed (by Test Priority)
Platform
Test Priority |  | Test Cases | QA Server | Staging Server | Production Server
Total |  | 31 | 30 | 3 | 0
| 5 | 4 | 4 | 0 | 0
| 4 | 6 | 6 | 0 | 0
| 3 | 21 | 20 | 3 | 0
| 2 | 0 | 0 | 0 | 0
| 1 | 0 | 0 | 0 | 0
| NA | 0 | 0 | 0 | 0
in Primary Platform
Executed | 30 |  | Executed | Not Executed
Not Executed | 1 | 5 | 4 | 0
|  | 4 | 6 | 0
|  | 3 | 20 | 1
|  | 2 | 0 | 0
|  | 1 | 0 | 0
|  | NA | 0 | 0
III. Summary of Current Test Results
Platform
Test Cases and Results |  |  |  | QA Server | Staging Server | Production Server
Total Number of Test Cases |  |  |  | 31 | 31 | 31
| Test Cases Executed or To Be Performed |  |  | 31 | 4 | 0
|  | Test Cases Executed |  | 30 | 3 | 0
|  |  | Passed | 24 | 2 | 0
|  |  | Failed | 6 | 1 | 0
|  | Test Cases Not Executed |  | 1 | 1 | 0
|  |  | Blocked | 0 | 1 | 0
| Test Cases Not To Be Performed |  |  | 0 | 27 | 31
|  |  | Deferred | 0 | 1 | 0
| % Test Cases Executed or To Be Performed (of Total Number of Test Cases) |  |  | 100% | 12.9% | 0%
|  | % Test Cases Executed (of Test Cases To Be Performed) |  | 96.77% | 75% | 0%
|  |  | % Passed (of Executed) | 80% | 66.67% | 0%
| QA Server | Staging Server | Production Server
Total Number of Test Cases | 31 | 31 | 31
Test Cases Executed or To Be Performed | 31 | 4 | 0
Test Cases Executed | 30 | 3 | 0
Passed | 24 | 2 | 0
Failed | 6 | 1 | 0
Blocked | 0 | 1 | 0
Test Cases Not Executed | 1 | 1 | 0
Test Cases Not To Be Performed | 0 | 27 | 31
Deferred | 0 | 1 | 0
Copyrighted 2010
NCI CBIIT
All Rights Reserved
Note on A3: Release Scope of Requirement/Test Case
Note on D3: Number of Requirements
Note on E3: Number of Test Cases
Note on F3: # of Requirements not mapped to a Test Case
Note on G3: # of Test Cases not mapped to a Requirement
Note on H3: % Mapped Requirements
Note on I3: % Mapped Test Cases
Note on A27: Number of Test Cases based on Test Priority
Note on D28: Primary, Secondary and Tertiary Platforms as defined in Project Summary worksheet
Note on A29: Test Priority on a scale of 1 to 5
Note on C29: # of Test Cases with this Priority
Note on D29: # of Test Cases executed on this platform
Note on E29: # of Test Cases executed on this platform
Note on F29: # of Test Cases executed on this platform
Note on B36: Not Available
Note on E57: Primary, Secondary and Tertiary Platforms as defined in Project Summary worksheet
Note on A59: = Test Cases To Be Performed + Test Cases Not To Be Performed
Note on B60: = Test Case Executed + Test Cases Not Executed
Note on C61: = Passed + Failed

## Project Summary
Project Information
General Information
Product: | caNanoLab
Release: | 1.5.2
Test Area: | caNanoLab
Test Case Owner: | David Li
Start Date: | 2010-07-01
Reference Documents:
System Test Platform Information
Primary Platform: | QA Server
Secondary Platform: | Staging Server
Tertiary Platform: | Production Server
Tier Dates
| Estimated | Actual
Enter QA Date:
Enter Stage Date:
Enter Prod Date:
Requirement Delivered Date
% Test Cases Developed
BDA Certified (Yes/No)
Tag Dates
Tag | Date Tag was Delivered | # Requirements Delivered
Test Plan
Small paragraph describing the plan to test this application. This may include what type(s) of testing will be used, the approach to testing, and other relevant details.
Project Summary Report
This paragraph should summarize the end result of testing. Fill out this paragraph when test execution is complete. Official approval is recorded in the Document History/Approval tab. Submit this same summary via email to PM, QA Manager, and other relevant team members.

## Test Cases
|  | Test Cases for: caNanoLab v1.5.2 | [9 empty] | QA Server | [8 empty] | Staging Server | [9 empty] | Production Server
Test Case ID | Test Description/Purpose | Test Priority | Procedure | Category/Module | PreRequisite | Expected Results | Requirement ID | Requirement Description | Requirement Reference | Release Scope | asdf | To Be Performed | Current Test Result | Actual Result | Date Executed | Build Tested | Tester | Defect ID | Defect Resolution Status | Prevent Release | To Be Performed | Current Test Result | Actual Result | Date Executed | Build Tested | Tester | Defect ID | Defect Resolution Status | Prevent Release | asdf | To Be Performed | Current Test Result | Actual Result | Date Executed | Build Tested | Tester | Defect ID | Defect Resolution Status | asdf
T_001 | The search samples test case allows users to verify searching the samples and download them | 5 | Click on the 'Search Samples' on the main page. Enter the search criteria for one or any of the following fields: keywords, name, point of contact, nanaomaterial entity, functionalizing entity, function, characterization type and characterization and click 'Search'. For example, use 'carbon', 'blood' or 'emulsion' as the keyword. View the results and click on sample name to check out the descriptions. | Regression Test |  | The User successfully searches for samples | Req_001 | Old Requirement |  | O |  | Y | P | Expected | 2010-09-14 | 1.5.2 | David Li
T_002 | The search protocols test case allows users to verify searching the protocols and download them | 5 | Click on the 'Search Protocols' on the main page. Enter the search criteria for one or any of the following fields: type, name, abbreviation and file title and click 'Search'. For example, use 'chemotaxis' or 'coagulation' for Protocol File Title. View the results and click on protocols listed in the file column which you wish to download. | Regression Test |  | The User successfully searches for and downloads protocols. | Req_002 | Old Requirement |  | O |  | Y | P | Expected | 2010-09-14 | 1.5.2 | David Li |  |  |  | d
T_003 | verify that PIs can submit samples data | 5 | Log into the caNanoLab application with PI privilege. The PI can then submit some data to the system. This goes to the curator for data review before they can be made public.The researcher can search and see this data, however because it is visible to him. | Regression Test | The User is logged into the System with PI credentials. Click on Submit Samples and follow through the procedures. | PI can submit new samples to the system | Req_003 | Old Requirement |  | N |  | Y | P | Expected | 2010-09-14 | 1.5.2 | David Li
T_004 | PIs can copy sample, modify and submit | 4 | Log into the caNanoLab application with PI privilege. The PI can look up some samples, click on edit, make a copy of it, modify the copy and submit the new data to the system. This goes to the curator for data review before they can be made public.The researcher can search and see this data, however because it is visible to him. | Regression Test | The User is logged into the System with PI credentials. | PI can copy a sample, modify it and submit the modified copy as a new sample to the system | Req_004 | Old Requirement |  | N |  | Y | P | Expected | 2010-09-14 | 1.5.2 | David Li
T_005 | verify that PIs can submit protocols data | 5 | Log into the caNanoLab application with PI privilege | Regression Test | The User is logged into the System with PI credentials. Click on Submit Protocols and follow through the procedures. | PI can submit new protocols to the system | Req_005 | Old Requirement |  | N |  | Y | P | Expected | 2010-09-14 | 1.5.2 | David Li
T_006 | Update Samples in the database | 4 | The User is logged into the System with the privilege to submit/update particle. After Login,click on the 'search samples' button on the menu bar and locate a previously submitted particle. Click this hyper-linked item in the search results and change the details which need to be updated. Click update at the bottom of the page. Search the particle again. Make sure information has been updated. | Regression Test | The User is logged into the System with submit/change credentials. | A message is shown informing that the update was successful. | Req_006 | New Requirement for this release |  | N |  | y | P | Expected | 2010-09-14 | 1.5.2 | David Li
T_007 | Update Protocls in the database | 4 | The User is logged into the System with the privilege to submit/update particle. After Login,click on the 'search protocols' button on the menu bar and locate a previously submitted protocol. Click edit next to this item in the search results and change the details which need to be updated. Click update at the bottom of the page. Search the protocols again. Make sure information has been updated. | Regression Test | The User is logged into the System with submit/change privileges. | A message is shown informing that the update was successful. | Req_007 | New Requirement for this release |  | N |  | y | F | Failed. When protocol version is changed, a new protocol is created with the old one still in the database. Is this intended? When you try to add access to protocol by adding a collaboration group, the collaboration information is lost when you click on save in access information. There is no confirmation message. Subsequent search of the protocol shows no collaboration group was saved. | 2010-09-14 | 1.5.2 | David Li
T_008 | An authorized user can add a new contact to a sample previously submitted. | 3 | Log into the caNanoLab application. Click on the 'Search' Button on the top horizontal menu bar and select Search Nanoparticlel. Enters search criteria and click Submit. Click the Nanoparticle of interest. Click on the 'Add' link next to the Point of Contact menu. Enter a new contact and click 'save'. Go back and search the same particle again. Verify the new contact info is saved. | Regression Test | The user is logged into the system and has the privilege to submit / modify data. | The System successfully saves the added new contact information. | Req_008 | Old Requirement |  | N |  | y | P | Expected | 2010-09-14 | 1.5.2 | David Li
T_009 | Submit a new sample by copying an existing sample and modify information as needed | 3 | The User is logged into the System and with the privilege to submit/update particle. After Login,click on the 'Samples' tab on the top menu bar. On the manage samples page that has been opened, click 'Copy an existing sample' under sample links. Search and find the sample you wish to copy, rename it and modify information as needed. Go back to the home page and search for this new sample in order to verify that it has been properly entered and saved. | Regression Test | The user is logged into the system and has the privilege to submit / modify data. | The System successfully saves information submitted for the new sample. | Req_009 | Old Requirement |  | O |  | y | P | Expected | 2010-09-14 | 1.5.2 | David Li |  |  |  | y | P |  | 2009-12-14 | 1.0 RC1 | Bob
T_010 | Help menu is available when submitting a new sample by copying an existing sample | 3 | The User is logged into the System and with the privilege to submit/update particle. After Login,click on the 'Samples' tab on the top menu bar. On the manage samples page that has been opened, click 'Copy an existing sample' under sample links. Click on the "Help" hyperlink on the upper right hand side. | Regression Test | The user is logged into the system and has the privilege to submit / modify data. | A help menu on the subject pops up with detailed instructions and hyperlinks. | Req_010 | Old Requirement |  | O |  | y | P | Expected | 2010-09-14 | 1.5.2 | David Li
T_011 | A user can no longer search remote caNanoLab nodes connected to the caBIG grid (caGrid) for available nanoparticle reports. | 3 | Click on the 'Remote ' tab on the menu bar and select 'Remote Report Search'. Stop here if the Remote tab is no longer there. Select the Node and other criteria including report title Grid Node Host, report type, particle type, function type and click 'Search'. | Regression Test |  | Remote tab no longer available | Req_011 | New Requirement for this release |  | N |  | Y | P | Expected | 2010-09-14 | 1.5.2 | David Li
T_012 | A public user does not need to log in. He can only view public data | 4 | The user does not log into the system. He merely goes to the search samples / search protocols / search publications page and go from there. The search results will be public data only. | Regression Test | No log in required. | The public user can read / search public data without logging in. No private data is visible to him. | Req_012 | Old Requirement |  | O |  | Y | P | Expected | 2010-09-14 | 1.5.2 | David Li |  |  |  | Y | b |  | 2009-12-14 | 1.0 RC1 | Bob | [8 empty] | 1.0 RC1 | Bob
T_013 | A Researcher can submit private data to the curator for review and search all private data assigned to him/her | 3 | The User is logged into the system as a researcher. After login,try to submit data click on the 'Search Samples' tab on the top menu bar. Search samples. Check to see if there are any private samples. At least private samples from the researcher should be visible. Go back to the search page and click on the "Search Protocols" tab. Search some protocols. Find a protocol or a sample that is private data visible to the researcher. | Regression Test | The user is logged in as a researcher. There are some private files in the database that the researcher has been assigned access (such as his/her own data, where access is default) | The researcher successfully finds some private data where he has the privilege to access. | Req_013 | Old Requirement |  | O |  | Y | P | Expected | 2010-09-14 | 1.5.2 | David Li |  |  |  | y | P |  | 2009-12-14 | 1.0 RC1 | Bob
T_014 | A researcher can update private data | 3 | The User is logged into the system as a researcher. After log-in, click on 'Search Samples' tab on the top menu bar. Check to see if there are any private samples. At least private samples from the researcher should be visible. Open the samples and update them. Go back to the search page and click on the "Search Protocols" tab. Search some protocols. Find a protocol that is private data visible to the researcher and update it. | Regression Test | The user is logged in as a researcher. There are some private files in the database that the researcher has been assigned access (such as his/her own data, where access is default) | The researcher successfully finds some private data where he has the privilege to update. | Req_014 | New Requirement for this release |  | N |  | Y | P | Expected | 2010-09-14 | 1.5.2 | David Li
T_015 | A researcher can delete private data | 3 | The User is logged into the system as a researcher. After log-in, click on 'Search Samples' tab on the top menu bar. Check to see if there are any private samples. At least private samples from the researcher should be visible. Open a sample and delete it. Go back to the search page and click on the "Search Protocols" tab. Search some protocols. Find a protocol that is private data to the researcher and delete it. | Regression Test | The user is logged in as a researcher. There are some private files in the database that the researcher has been assigned access (such as his/her own data, where access is default) | The researcher successfully finds some private data where he has the privilege to delete. | Req_015 | New Requirement for this release |  | N |  | Y | P | Expected | 2010-09-14 | 1.5.2 | David Li
T_016 | A researcher can submit a publication and associate it to a particular sample | 3 | The User is logged into the system as a researcher. After log-in, click on 'Publications' tab on the top menu bar. Click on submit a new publication link. The publication submission page should open. Fill in all the required information. Also try assigning a sample to the publication. Click on submit. If you get a message that submission was successful, go back to the search page and click on the "Search Publications" link. Find the publication and verify that it was saved. | Regression Test | The user is logged in as an investigator or data curator. There are some private files in the database that the researcher has been assigned access (such as his/her own data, where access is default) | The investigator successfully submits the publication. | Req_016 | New Requirement for this release |  | N |  | Y | F | Unable to add access to the publication. When a collaboration group is selected, clicking the save button loses the collaboration group information. There is no confirmation message nor is the collaboration group saved. | 2010-09-14 | 1.5.2 | David Li
T_017 | A researcher can manage publication data | 3 | The User is logged into the system as a researcher. After log-in, click on 'Publications' tab on the top menu bar. Click on search publications link. At least private publications from the researcher should be visible. Open a publication and modify the content. Click on update and save the change. Go back to the search page and click on the "Search Publications" link. Find the publication and verify the changes. | Regression Test | The user is logged in as a researcher. There are some publications in the database that the researcher has been assigned access (such as his/her own submission, where access is default) | The researcher successfully updates the publication. | Req_017 | New Requirement for this release |  | N |  | Y | P | Unable to add access to the publication. When a collaboration group is selected, clicking the save button loses the collaboration group information. There is no confirmation message nor is the collaboration group saved. | 2010-09-14 | 1.5.2 | David Li
T_018 | A Researcher can manage collaboration groups | 4 | The User is logged into the system as a researcher. After Login,click on the 'Manage Collaboration Groups' tab on the top menu bar. From the next page, he can modify information on existing collaboration groups or create new ones. | Regression Test | The user is logged in as a researcher. | The researcher successfully updates information on existing collaborations groups and sets up a new collaboration group. | Req_018 | New Requirement |  | N |  | Y | P | Expected | 2010-09-14 | 1.5.2 | David Li
T_019 | A Researcher can manage users in a collaboration group | 4 | The user is logged into the system as a researcher. After Login,click on the 'Manage Collaboration Groups' tab on the top menu bar. From the next page, he can modify user information in an existing collaboration groups or create new ones for the collaboration group. | Regression Test | The user is logged in as a researcher. | The researcher successfully updates information on existing user accounts and sets up new accounts in the community tab. | Req_019 | New Requirement |  | N |  | Y | F | When changing user access to group from read to read update delete, the access status in brackets under user access to group stays unchanged although the information has been saved via clicking save. Submission and subsequent search of collaboration group verifies this change. Johndoe/test jbh/Sharon: Unexpected Exception: Error finding existing collaboration groups accessible by the user. | 2010-09-14 | 1.5.2 | David Li
T_020 | A curator can create data | 3 | The User is logged into the system as a curator. After login,click on the 'Submit Protocols" page and submit an protocol. Also click on " Submit Samples" page and submit a sample. | Regression Test | The user is logged in as a curator of the data. | Data is successfully created | Req_020 | New Requirement |  | N |  | Y | F | Unable to add access to sample. When a collaboration group is selected, clicking the save button loses the collaboration group information. There is no confirmation message nor is the collaboration group saved. | 2010-09-14 | 1.5.2 | David Li
T_021 | A curator can update data | 3 | The User is logged into the system as a curator. After log-in,click on the 'Update Protocols" page and update an protocol. Pick some private data and modify them too. Also click on " Update Samples" page and update a sample. | Regression Test | The user is logged in as a curator of the data. | Data is successfully updated | Req_021 | New Requirement |  | N |  | Y | F | Unable to add access to sample. When a collaboration group is selected, clicking the save button loses the collaboration group information. There is no confirmation message nor is the collaboration group saved. | 2010-09-14 | 1.5.2 | David Li
T_022 | A curator can delete data | 3 | The User is logged into the system as a curator. After log-in,click on the 'Search Protocols" page and delete a test protocol. Pick some private protocol and make sure this works with private files. Also click on " Search Samples" page and delete a sample. | Regression Test | The user is logged in as a curator of the data. | Data is successfully deleted | Req_022 | New Requirement |  | N |  | Y | P | Expected | 2010-09-14 | 1.5.2 | David Li
T_023 | A curator can review private data and make them public | 3 | The User is logged into the system as a curator. After log-in,click on the 'Search Samples' tab on the top menu bar. Search samples. Go back to the search page and click on the "Search Protocols" tab. Search some protocols. Find a protocol or a sample that is private data. Review the information, update it and click Add Access and choose add collaboration group (public) and select read option. Click save on the page. | Regression Test | The user is logged in as a curator of the data. | The curator successfully makes private data public | Req_023 | New Requirement |  | N |  | Y | P | Expected | 2010-09-14 | 1.5.2 | David Li |  |  |  | Y | f |  | 2009-12-14 | 1.0 RC1 | Bob
T_024 | A curator can delete public sample | 3 | When logged in as a data curator, user can search public samples, click edit and delete existing data. | Regression Test | The user is logged in as a data curator. | Data is successfully deleted | Req_024 | New Requirement |  | N |  | Y | P | Expected | 2010-09-14 | 1.5.2 | David Li
T_025 | An administrator can add user | 3 | When logged in as an administrator, user can click on the Administration tab on the top menu to bring up the Administration links. Choose Create User Accounts and Assign Privileges. Log in again. Click on Users when the UPT Tool comes up. Click on Search Existing Users to verify that a new user has been successfully created. | Regression Test | The user is logged in as an administrator | New user is added successfully | Req_025 | New Requirement |  | N |  | Y | P | Expected | 2010-09-14 | 1.5.2 | David Li
T_026 | An administrator can update user info | 3 | When logged in as an administrator, user can click on the Administration tab on the top menu to bring up the Administration links. Choose Create User Accounts and Assign Privileges. Log in again. Click on Users when the UPT Tool comes up. Click on Select an Existing User. If user unknown, search with no criteria returns all users. Select user of interest, click view details to bring up user information. Click update to save any change. | Regression Test | The user is logged in as an administrator | User info is updated successfully | Req_026 | New Requirement |  | N |  | Y | P | Expected | 2010-09-14 | 1.5.2 | David Li
T_027 | An administrator can add group | 3 | When logged in as an administrator, user can click on the Administration tab on the top menu to bring up the Administration links. Choose Create User Accounts and Assign Privileges. Log in again. Click on Groups when the UPT Tool comes up. Click on Create a New Group to do so. | Regression Test | The user is logged in as an administrator | Group info is created successfully | Req_027 | New Requirement |  | N |  | Y | P | Expected | 2010-09-14 | 1.5.2 | David Li
T_028 | An administrator can create new group | 3 | When logged in as an administrator, user can click on the Administration tab on the top menu to bring up the Administration links. Click on groups and then Create a New Group.Log in again. Click on Groups when the UPT Tool comes up. Click on Select an Existing Group. If group unknown, search with no criteria returns all groups. Select group of interest, click view details to bring up group information. Verify the group info was saved correctly. | Regression Test | The user is logged in as an administrator | Group was created successfully | Req_028 | New Requirement |  | N |  | Y | P | Expected | 2010-09-14 | 1.5.2 | David Li
T_029 | An administrator can update group info | 3 | When logged in as an administrator, user can click on the Administration tab on the top menu to bring up the Administration links. Choose Create User Accounts and Assign Privileges. Log in again. Click on Groups when the UPT Tool comes up. Click on Select an Existing Group. If group unknown, search with no criteria returns all groups. Select group of interest, click view details to bring up group information. Click update to save any change. | Regression Test | The user is logged in as an administrator | Group info is updated successfully | Req_029 | New Requirement |  | N |  | Y | P | Expected | 2010-09-14 | 1.5.2 | David Li
T_029 | Regenerate all data matrices | 3 | Log into caNanoLab as a curator. Go to the Curation tab on top of the page. Click the Manage Batch Data Availabiligy link. Choose Re-generate data availablility for samples with existing data avaialabiligy. | Regression Test | The user is logged in as a data curator |  | Req_029 | New Requirement |  | N |  | Y | F | Termintated with error | 2010-09-27 | 1.5.2 | David Li
T_030 | Transfer of ownership | 3 | Log into caNanoLab as a curator. Go to the Administration tab on top of the page. Click the Transfer Data Ownership link. Give current owner login name and new owner login name. Choose data type, click submit. |  | The user is logged in as a data curator | Sample/protocol/publication ownership is transferred from one user to another when checked | Req_030 |  |  | N |  | Y
caNanoLab Grid Services
Note on A2: Unique ID for Test
Note on B2: Short description or purpose of Test Case
Note on C2: Priority on a scale of 1 to 5
Note on D2: Steps for performing the Test Case
Note on E2: Category or Module of the Test Case
Note on F2: Pre-existing condition that must be met
Note on G2: Expected Result of steps performed in the Test
Note on H2: Unique ID for Requirement
Note on I2: Short description of Requirement
Note on J2: Reference to a source for the Requirement
Note on K2: Is the Requirement new in this Release?
Note on M2: Is this Test Case going to be performed?
Note on N2: Current test result for the latest build tested
Note on O2: Actual test result for each build tested
Note on P2: Date Test Case was executed
Note on Q2: Name of the Build tested on
Note on R2: Name of the person who performed the Test
Note on S2: Defect ID for Defect found during testing
Note on T2: Status on how the Defect is being resolved
Note on U2: Severity of the Defect on a scale of 1 to 5
Note on W2: Is this Test Case going to be performed?
Note on X2: Current test result for the latest build tested
Note on Y2: Actual test result for each build tested
Note on Z2: Date Test Case was executed
Note on AA2: Name of the Build tested on
Note on AB2: Name of the person who performed the Test
Note on AC2: Defect ID for Defect found during testing
Note on AD2: Status on how the Defect is being resolved
Note on AE2: Severity of the Defect on a scale of 1 to 5
Note on AG2: Is this Test Case going to be performed?
Note on AH2: Current test result for the latest build tested
Note on AI2: Actual test result for each build tested
Note on AJ2: Date Test Case was executed
Note on AK2: Name of the Build tested on
Note on AL2: Name of the person who performed the Test
Note on AM2: Defect ID for Defect found during testing
Note on AN2: Status on how the Defect is being resolved

## Document History and Approval
Document History and Approval
Record milestone changes and approval to this document including: * Submission to DEV * DEV Suggested Revisions * QA modification from DEV recommendations * DEV Approval * Submission to Project Manager * Project Manager Approval * Test Execution Complete - submitted to PM and QA Manager * Review of document * QA Manager Approval
Modified/Approved By | Date | Team/Role | Notes/Approval
DEV team | 2010-08-15 | DEV
qaProject Template
Version | 2.1.0
Last Updated | 2010-04-06
Changes from 2.0.3 | Rearranged columns in Test Cases worksheet; Moved Test Case columns to the left so that the User may freeze the first two columns (Test Case ID and Test Description/Purpose); Adjusted formulas in Dashboard Summary
Added light yellow background color to Test Priority column to indicate that it's a column that affects formulas in the Dashboard Summary
Changed background color of third testing platform (Production) so that it's not the same background color as the first set of columns

## Test Environment
Test Environment
QA Server
OS: | Development tier - Solaris (Unix)
Application Server: | JBoss 4.0.2
Database: | MySQL v4.1.19, Oracle
Java Technologies: | Hibernate 3.0.5, Log4j 1.2.8
Web Browser: | IE 5.0+, Mozilla 1.0
Other
Staging Server
OS: | Windows 2000
Application Server: | JBoss 4.0.2
Database: | MySQL v4.1.19, SQL Server 2000, Tomcat
Java Technologies: | Hibernate 3.0.5, Log4j 1.2.8
Web Browser: | IE 5.0+, Mozilla 1.0
Other
Production Server
OS: | Windows 2000
Application Server: | JBoss 4.0.2
Database: | MySQL v4.1.19, SQL Server 2000, Tomcat
Java Technologies: | Hibernate 3.0.5, Log4j 1.2.8
Web Browser: | IE 5.0+, Mozilla 1.0
Other